Academic Consultant

## Outputs and tentative schedule

| Outputs | No of days | June | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | March |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Meeting with the project team | ½ |  |  |  |  |  |  |  |  |  |  |
| Review the existing recordings of the Teachers’ Continuing Professional Development Webinar Series and design tasks for fortnightly quizzes and evaluate the responses | 15 days |  |  |  |  |  |  |  |  |  |  |
| Design and deliver monthly Teachers’ Continuing Professional Development Webinar Series (session planning and delivery) | 8.5 days |  |  |  |  |  |  |  |  |  |  |
| Review the audio lessons and prepare a general guidance document on the audio resources | 4 days |  |  |  |  |  |  |  |  |  |  |
| Design and deliver 4 sessions on how to use the audio lessons in the classroom (session planning and delivery) | 4 days |  |  |  |  |  |  |  |  |  |  |
| Support the local consultant to deliver sessions | 3 days |  |  |  |  |  |  |  |  |  |  |

We anticipate 35 days of consultancy time for this role.