**School Holidays in Ile de France 2019**

|  |  |
| --- | --- |
| Winter Holidays | End of courses: Saturday 23 February 2019 Start of courses: Monday 11 March 2019 |
| Spring Holidays | End of courses : Saturday 20 April 2019 Start of courses : Monday 6 May 2019 |

|  |  |
| --- | --- |
| **Creteil has 120 Primary Teachers in total to be trained during the school holidays**  **Versailles has 70 Primary Teachers and 25 Secondary Teachers to be trained in the school term**  **Groups size will be a maximum of 20** | |
| **Approximate schedule** for delivery of training to fit in or around French Education Zone C school holidays.  N.B. 5-day courses for Creteil will take place during school holidays. The 5-day courses for Versailles delivered in two parts i.e. 2 days and 3 days blocks will take place during the school year; Part 1 is immediately before or after the winter school holidays and Part 2 is in May.  Groups will have 20 teachers as a recommended maximum | |
| **Date** | **Training to be delivered** |
| 4-6 weeks before training | English language assessment for Teachers : Testing English to CEFR levels of all teachers by (British Council) and a CLIL baseline survey will be done by all trainees; enabling the groups below to be formed according to assessment & baseline results. |
| February 2019  Week of  11 Feb | **Versailles**  **1 groups of secondary teachers:** Part 1, which is two days (12hrs) of their total five days (30hrs) intensive CLIL & English training approximate CEFR level B1/B2  (Partner to deliver)  **2 groups of primary teachers:**  Part 1, which is two days (12hrs) of their total five days (30hrs) intensive CLIL & English training approximate CEFR B1/B2 (Partner to deliver) |
| February 2019  Week of  18 Feb | **Versailles**  **1 groups of secondary teachers:** Part 1, which is two days (12hrs) of their total five days (30hrs) intensive CLIL & English training approximate CEFR level B1/B2  (Partner to deliver)  **2 groups of primary teachers:**  Part 1, which is two days (12hrs) of their total five days (30hrs) intensive CLIL & English training approximate CEFR B1/B2  (Partner to deliver) |
| February 2019  School Holiday  Week of  25 Feb | **Creteil – First cohort of 3 groups of primary teachers:** 5 days (30hrs) intensive CLIL & English training approximate CEFR B1/B2  (Partner to deliver) |
| February 2019  School Holiday  Week of  4 March | **Creteil – First cohort of 3 groups of primary teachers:** 5 days (30hrs) intensive CLIL & English training approximate CEFR B1/B2  (Partner to deliver) |
| May 2019  Week of  6 May | **Versailles**  **1 group of secondary teachers: Part 2**, which is 3 days (18hrs) of their total 5 days (30hrs) intensive CLIL & English training approximate CEFR level B1/B2  (Partner to deliver)  **2 groups of primary teachers:** **Part 2,** which is 3 days (18hrs) of their total 5 days (30hrs) intensive CLIL & English training approximate CEFR B1/B2  (Partner to deliver) |
| May 2019  Week of 13 May | **Versailles**  **1 group of secondary teachers: Part 2**, which is 3 days (18hrs) of their total 5 days (30hrs) intensive CLIL & English training approximate CEFR level B1/B2  (Partner to deliver)  **2 groups of primary teachers:** **Part 2,** which is 3 days (18hrs) of their total 5 days (30hrs) intensive CLIL & English training approximate CEFR B1/B2  (Partner to deliver) |